## README
Last Update | 2018-11-09
Author | Cheng Chen
Email
Description | Team: Taskers (Cheng Chen)
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | User Registration and Login / Logout | No matter as a customer or restaurant manager interested by Tasks, I want to register so I can login/logout and do further function, and as a registered user, I want to be able to login to fully use the website and to logout once I’m done. | 3 | 2
2 | Menu | As a registered customer, I want to be able to see the menu of a particular restaurant by clicking into it. As a registered restaurant, I want to create my menu and be able to edit it. | 3 | 1
3 | Review Tasks | As a registered customer, I want to be able to order my meals by selecting the meals and the number of each meals. To make sure the order is correct, I should be able to review the order and make some changes before submitting it into database. As a registered restaurant, I should be able to see the order made to our restaurant. | 4 | 3
| Total |  | 10
Note on C2: Acceptance criteria : - The customer should be able to register with username, choose a username and set a password. -The restaurant should be able to register with account name, name, address, logo picture to be display. - Registered users will log in with their username and their password - Registered users can log out by clicking the log out. - Registered restaurants should be showed for customer.
Note on C3: Acceptance criteria : - Customer can view the menu of each registered restaurant. - Restaurant should be able to create the meals by submitting name, price, and picture. - Restaurant can update or change the information of the meals.
Note on C4: Acceptance criteria : - Customer should be able to initialize order from the menu page by selecting the meal and number of it. - Customer should be able to review the order and make some changes including modify the number of each meals or delete the whole meal from the order. - Restaurant can view the order made to them by customers. Including the name of the customer and meals and number of it.

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: create menu
Task 2: modify menu
Task 3: display menu
Note on A2: Task1: restaurant can create menu for itself Acceptance critria: 1. restaurant can add meals by upload the picture, price and name of the meal.
Note on A3: Task1: restaurant can modify own menu Acceptence criteria: 1.restaurant can change the name, price and the picture of meal. 2. restaurant can completely delete a meal.
Note on A4: Task 3: customer should be able to view the menu acceptance criteria: 1. customer should be able to view the correct information of menu, including price, name and picture of all meals

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Cheng Chen | 5

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 10 | 0 | 0 | 10 | 10
1 | 10 | 3 | 3 | 7 | 7
2 | 10 | 0 | 3 | 7 | 4